## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team and Freshman Seminar acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions, cross-team testing, and Freshman Seminar testing.
Team Name | "team-swen-261-06-b error451"
Testing Team Name | fill in when doing cross-team or Freshman Seminar testing

## Test Plan
User Story | Acceptance Criterion | Sprint 1 | Tester initials; date; comments (required if test failed) | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a Developer I WANT to submit a request to get a single User SO THAT I can access the name and information of the user | GIVEN I submit a request for a user WHEN the user exists THEN the system should return that user and a status code of 200 (OK) |  |  | Pass | TN; 3/15/22 | Pass | TN; 3/31/2022
| GIVEN I submit a request for a user WHEN the user does not exist THEN the system should return a status code of 404 (NOT_FOUND) |  |  | Pass | TN; 3/15/22 | Pass | TN; 3/31/2022
AS a Developer I WANT submit a request to alter user information so THAT the website has the most up to date information about the users. | 1. GIVEN I attempt a user update WHEN that user exists THEN the system should change the user information and return a status code of 200 (OK) |  |  | Pass | TN; 3/15/22 | Pass | TN; 3/31/2022
| 2. GIVEN I attempt a user update WHEN that user does not exist THEN the system should add the user information and return a status code of 200 (OK) |  |  | Pass | TN; 3/15/22 | Pass | TN; 3/31/2022
AS a Developer I WANT to submit a request to get the users in the whose name contains the given text SO THAT I have access to only those users. | 1. GIVEN I submit a request for a user WHOSE name contains the given text THEN the system should return a list of users that contain the text specification and a status code of 200 (OK). |  |  | Pass | TN; 3/15/22 | Pass | TN; 3/31/2022
| 2. GIVEN I submit a request for a user WHOSE name does not contain the given text THEN the system should return an empty list of users and a status code of 200 (OK). |  |  | Pass | TN; 3/15/22 | Pass | TN; 3/31/2022
As a Developer I want to submit a request to delete a single user SO THAT it is no longer in the users persistence file. | GIVEN I submit a request to delete a single user WHEN the user exists THEN the system should delete the user from the inventory and return a status code of 200 (OK) |  |  | Pass | TN; 3/15/22 | Pass | TN; 3/31/2022
| GIVEN I submit a request to delete a single user WHEN the user does not exist THEN the system should return a status code of 404 (NOT_FOUND) |  |  | Pass | TN; 3/15/22 | Pass | TN; 3/31/2022
AS a Developer I WANT to submit a request to create a new user SO THAT it is available to in the users persistence file | GIVEN I submit a user object WHEN no user with the given name exists THEN the system should create the user, save to the persistent store, and return the user object and a status code of 201 (CREATED) |  |  | Pass | TN; 3/15/22 | Pass | TN; 3/31/2022
| GIVEN I submit a user object WHEN a user with the given name already exists THEN the system should return a status code of 409 (CONFLICT) |  |  | Pass | TN; 3/15/22 | Pass | TN; 3/31/2022
As an admin, I want to update products so that the product listing reflects their actual prices and quantities. | **Given** a product is listed **when** I change the price/quantity**then** the product's listing should update with that change. |  |  | Pass | TN; 3/15/22 | Pass | TN; 3/31/2022
As a buyer I want to be able to chose which features to customize so I can get a personalized and unique product. | **Given** that a product is available **when** I am viewing the product **then** I expect to see options of wood types |  |  | Pass | TN; 3/15/22 | Pass | TN; 3/31/2022
| **Given** that a product is available **when** I am viewing the product **then** I expect to see an option to have my custom text engraved |  |  | Pass | TN; 3/15/22 | Pass | TN; 3/31/2022
| **Given** that a product is available **when** I am viewing the product **then** I expect to see options of wood varnishes |  |  | Pass | TN; 3/15/22 | Pass | TN; 3/31/2022
| **Given** that a product is available **when** I am viewing the product **then** I expect to see an option to add to shopping cart |  |  | Pass | TN; 3/15/22 | Pass | TN; 3/31/2022
| **Given** that a wood type is not selected **when** I try to add to shopping cart **then** I expect to stay on the product-detail page and receive a message telling me to select a type of wood |  |  | Pass | TN; 3/15/22 | Pass | TN; 3/31/2022
| **Given** that a varnish type is not selected **when** I try to add to shopping cart **then** I expect to stay on the product-detail page and receive a message telling me to select a type of varnish |  |  | Pass | TN; 3/15/22 | Pass | TN; 3/31/2022
As a buyer I want to log in as a customer so that I can make purchases. | **Given** that I already have an account on the website, **when** I enter my username, **then** I expect to be able to access my account info. |  |  | Pass | TN; 3/15/22 | Pass | TN; 3/31/2022
| **Given** that I already have an account on the website, **when** I enter my username, **then** I expect to be able to access my shopping cart (and anything I had previously put in it) |  |  | Fail | TN; 3/15/22: user sees other user's products too | Pass | TN; 3/31/2022
| **Given** that I already have an account on the website, **when** I enter my username, **then** I expect to be able to access the website. |  |  | Pass | TN; 3/15/22 | Pass | TN; 3/31/2022
| **Given** that I am logged in **when** I am done with my purchase **then** I should have an option to logout. |  |  | Pass | TN; 3/15/22 | Pass | TN; 3/31/2022
| **Given** that I use **admin** as my usename **when** I login, **then** I should be given the owner view of the site. |  |  | Pass | TN; 3/15/22 | Pass | TN; 3/31/2022
| **Given** that I do not use **admin** as my usename **when** I login, **then** I should be given the buyer view of the site. |  |  | Pass | TN; 3/15/22 | Pass | TN; 3/31/2022
As a Buyer I want to see a list of products so that I can choose what to purchase. | As a Buyer I want to see a list of products so that I can choose what to purchase. |  |  | Pass | TN; 3/15/22 | Pass | TN; 3/31/2022
| **Given** that a certain product is out of stock **when** I see the product while browsing **then** I expect the product to be listed as unavailable. |  |  | Fail | TN; 3/15/22 | Pass | TN; 3/31/2022
As an admin, I want to be able to add and delete products from my site's listing so that the site represents my inventory. | **Given** a product's name is filled in**when** I click the add product button **then** I expect the new product to be listed. |  |  | Pass | TN; 3/15/22 | Pass | TN; 3/31/2022
| **Given** a product's name is not filled in**when** I click the add product button **then** I expect the new product to not be listed. |  |  | Pass | TN; 3/15/22 | Pass | TN; 3/31/2022
| **Given** a product is listed**when** I click the delete button **then** I expect the product to be removed from inventory and no longer listed. |  |  | Pass | TN; 3/15/22 | Pass | TN; 3/31/2022
As a customer I want to add products to a shopping cart so that I can go to the Checkout page and finish purchase (Button). | GIVEN I attempt to add a product to my cart WHEN that product exists in the inventory THEN the system should add the product to the shopping cart and return a status code of 200 (OK) |  |  | Pass | TN; 3/15/22 | Pass | TN; 3/31/2022
As a customer I want to remove products from my cart so that I can change my shopping cart. | GIVEN I submit a request to delete a single product WHEN the product exists THEN the product should be removed from my cart |  |  | Pass | TN; 3/15/22 | Pass | TN; 3/31/2022
AS a Developer I WANT to submit a request to create a new product (name, price, quantity) SO THAT it is available to in the inventory | GIVEN I submit a product object WHEN no product with the given name exists THEN the system should create the product, add it to the inventory, save to the persistent store, and return the product object and a status code of 201 (CREATED) | Fail | TN; 2/14/22 It did meet the acceptance criteria, but there was an issue with one of our unit tests for it | Pass | TN; 3/15/22
| GIVEN I submit a product object WHEN a product with the given name already exists THEN the system should return a status code of 409 (CONFLICT) | Pass | TN; 2/14/22 | Pass | TN; 3/15/22
AS a Developer I WANT submit a request to alter product information so THAT the website provides the best information about the products. | 1. GIVEN I attempt a product update WHEN that product exists in the inventory THEN the system should change the product information and return a status code of 200 (OK) | Pass | TN; 2/14/22 | Pass | TN; 3/15/22
| 2. GIVEN I attempt a product update WHEN that product does not exist in the inventory THEN the system should add the product information and return a status code of 200 (OK) | Pass | TN; 2/14/22 | Pass | TN; 3/15/22
AS a Developer I WANT to submit a request to get a single product SO THAT I can access the price and quantity | GIVEN I submit a request for a product WHEN the product exists in the inventory THEN the system should return that product and a status code of 200 (OK) | Pass | TN; 2/14/22 | Pass | TN; 3/15/22
| GIVEN I submit a request for a product WHEN the product does not exist in the inventory THEN the system should return a status code of 404 (NOT_FOUND) | Pass | TN; 2/14/22 | Pass | TN; 3/15/22
_AS a Developer I WANT to submit a request to get the entire inventory SO THAT I have access to all of the products._ | 1. GIVEN I submit a request for the inventory WHEN products exist in the inventory THEN the system should return a list of products and a status code of 200 (OK) | Pass | TN; 2/14/22 | Pass | TN; 3/15/22
| 2. GIVEN I submit a request for the inventory WHEN no products exist in the inventory THEN the system should return an empty list of products and a status code of 200 (OK) | Pass | TN; 2/14/22 | Pass | TN; 3/15/22
As a Developer I want to submit a request to delete a single product SO THAT it is no longer in the inventory | GIVEN I submit a request to delete a single product WHEN the product exists THEN the system should delete the product from the inventory and return a status code of 200 (OK) | Pass | TN; 2/14/22 | Pass | TN; 3/15/22
| GIVEN I submit a request to delete a single product WHEN the product does not exist THEN the system should return a status code of 404 (NOT_FOUND) | Pass | TN; 2/14/22 | Pass | TN; 3/15/22
_AS a Developer I WANT to submit a request to get the products in the inventory whose name contains the given text SO THAT I have access to only those products. | 1. GIVEN I submit a request for a product in the inventory WHOSE name contains the given text THEN the system should return a list of products that contain the text specification and a status code of 200 (OK). | Pass | TN; 2/14/22 | Pass | TN; 3/15/22
| 2. GIVEN I submit a request for a product in the inventory WHOSE name does not contain the given text THEN the system should return an empty list of products and a status code of 200 (OK). | Pass | TN; 2/14/22 | Pass | TN; 3/15/22
As a buyer I want to refine the list of products so that I can view products best fitted to my wants. | **Given** I want to filter the products that I see **when** I choose a filter **then** the list of products on my browse page should be adjusted. |  |  |  |  | Pass | AR; 3/31/2022
As a CUSTOMER I want to only be able to add the max quantity of products to my shopping cart. | **Given** I add the max number of a single product to my shopping cart**when** I try to add another of that same product **then** I want to be shown an error and will not add to shopping cart |  |  |  |  | Pass | AR; 3/31/2022
| Given I add a product to my shopping cart when it is the last of its type then the product will be listed as out of stock |  |  |  |  | Pass | AR; 3/31/2022
As a customer I want to confirm my order so that I can finish my transaction. | **Given** that there are items in my cart and that the number of each item does not exceed the amount of that item that is present in inventory, **when** I checkout, **then** I expect that my shopping cart will be emptied. |  |  |  |  | Pass | TN; 3/31/2022
As a customer I want to see a aesthetically pleasing website so I feel more comfortable purchasing goods from it. | **Given** I access the website **when** I look around the various pages **then** I expect a uniform and professional look for the whole website. |  |  |  |  | Pass | TN; 3/31/2022
As a customer I want an error message when my login fails so I know my login information was wrong. As a new user I want an error message when my sign up fails so I know the username is already in use. | **Given** I try to login to the website **when** I use a login that is not a username in the database **then** I expect an error message that tells me my login is incorrect. |  |  |  |  | Pass | AR; 3/31/2022
| **Given** I try to sign up for the website **when** I use a username that is already in the database **then** I expect an error message that tells me my username is taken. |  |  |  |  | Pass | AR; 3/31/2022